## Lead Appointed Party
Project No: |  | Information management assignment matrix: Main Contractor (Lead Appointed Party)
Key: R Responsible for undertaking activity/task A Accountable for activity/task completion C Consulted during activity/task I Informed following activity/task completion |  |  | Appointing party |  | Lead appointed party | [6 empty] | Appointed party
|  | Source | Client | Client's third party | Bid coordinator | Lead Designer | Project manager | Quantity surveyor | CDM Principle Designer | Document controller | BIM Manager | Consultant and subcontractor task teams
ID | Activity/task
4 | Information management process - Appointment | ISO 19650- 2; 5.4
4.1 | Confirm the delivery team's BIM execution plan. | ISO 19650-2; 5.4.1
4.1.1 | Develop the delivery team's BIM execution plan in agreement with the supply chain, including: | ISO 19650-2; 5.4.1 |  |  |  | C | I |  |  |  | A/R | C
4.1.2 | Confirm the names of the individual(s) who will undertake the information management function. | ISO 19650-2; 5.4.1 a) |  |  | C | C | C |  |  | I | A/R | C
4.1.3 | Update the delivery team's information delivery strategy (as required). | ISO 19650-2; 5.4.1 b) | [8 empty] | A/R | C
4.1.4 | Update the delivery team's high-level responsibility matrix (as required). | ISO 19650-2; 5.4.1 c) | [8 empty] | A/R | C
4.1.5 | Confirm and document the delivery team's proposed information production methods and procedures | ISO 19650-2; 5.4.1 d) | [8 empty] | A/R | C
4.1.6 | Agree with the appointing party any additions or amendments to the project's information standard | ISO 19650-2; 5.4.1 e) | C |  |  | C |  |  |  |  | A/R | I
4.1.7 | Confirm the schedule of software, hardware and IT infrastructure the delivery team will use | ISO 19650-2; 5.4.1 f) |  |  |  | C | C | I | I | I | A/R | C
4.2 | Establish the delivery team's detailed responsibility matrix | ISO 19650- 2; 5.4.2
4.2.1 | Refine the high-level responsibility matrix to establish the detailed responsibility matrix | ISO 19650-2; 5.4.2 |  |  |  | R | C | I |  |  | A/R
4.2.2 | Share the detailed responsibility matrix for supply chain review and comment | n/a |  |  |  | R |  | I |  | R | A/R | C
4.3 | Establish the lead appointed party's exchange information requirements | ISO 19650- 2; 5.4.3
4.3.1 | Establish the lead appointed party's exchange information requirements | ISO 19650-2; 5.4.3 |  |  |  | A/R |  |  |  | I | R
4.3.2 | Define each information requirement | ISO 19650-2; 5.4.3 a) |  |  |  | A/R |  |  |  | I | R
4.3.3 | Establish the level of information need required to meet each information requirement | ISO 19650-2; 5.4.3 b) |  |  |  | A/R |  |  |  | I | R
4.3.4 | Establish the acceptance criteria for each information requirement | ISO 19650-2; 5.4.3 c) |  |  |  | A/R |  |  |  | I | R
4.3.5 | Establish the dates, relative to the project's information delivery milestones | ISO 19650-2; 5.4.3 d) |  |  |  | A/R |  |  |  | I | R
4.3.6 | Establish the supporting information that the appointed part might need, to fully understand or evaluate each information requirement or its acceptance criteria | ISO 19650-2; 5.4.3 e) |  |  |  | R |  |  |  | I | A/R
4.4 | Establish the task information delivery plan(s) | ISO 19650- 2; 5.4.4
4.4.1 | Establish a task information delivery plan template (if not provided by the appointing party within any shared resources) | n/a | [7 empty] | I | A/R
4.4.2 | Establish and maintain a task information delivery plan throughout the appointment | ISO 19650-2; 5.4.4 |  |  |  | C | I |  |  | I | C | A/R
4.5 | Establish the master information delivery plan | ISO 19650- 2; 5.4.5
4.5.1 | Aggregate task information delivery plans from each task team to establish the delivery team's master information delivery plan (MIDP) | ISO 19650-2; 5.4.5 |  |  |  | R |  |  |  |  | A/R | I
4.5.2 | Baseline deliverables and dates within the master information delivery plan | ISO 19650-2; 5.4.5 | [9 empty] | I
4.5.3 | Inform each task team and notify if any changes are required to the task information delivery plan | ISO 19650-2; 5.4.5 |  |  |  | R | A/R |  |  |  | I | I
4.5.4 | Inform the appointing party of any risks or issues which could impact on the project delivery milestones | ISO 19650-2; 5.4.5 | I |  |  | C | A/R |  |  |  | C | C
4.6 | Update shared resources | n/a
4.6.1 | Update the project’s information standard with agreed additions or amendments proposed by lead appointed parties within their pre- appointment BIM execution plans and subsequently throughout their appointment (including any updates required by the security management plan) | n/a | A/R |  |  | I | I |  |  | I | I | I
4.6.2 | Update the project’s information production methods and procedures with agreed additions or amendments proposed by lead appointed parties within their pre-appointment BIM execution plans and subsequently throughout their appointment (including any updates required by the security management plan) | n/a | A/R |  |  | I | I |  |  | I | I | I
4.7 | Complete lead appointed party's appointment documents | ISO 19650- 2; 5.4.6
4.7.1 | Complete lead appointed party's appointment documents | ISO 19650-2; 5.4.6 | A/R |  |  | I |  | I |  |  | I
4.7.2 | Ensure the appointing party's exchange information requirements are included in the appointment | ISO 19650-2; 5.4.6 | A/R |  |  | I |  | I |  |  | I
4.7.3 | Ensure the project's information standard is included in the appointment with any agreed additions or amendments | ISO 19650-2; 5.4.6 | A/R |  |  | I |  | I |  |  | I
4.7.4 | Ensure the project's information production methods and procedures is included in the appointment with any agreed additions or amendments | ISO 19650-2; 5.4.6 | A/R |  |  | I |  | I |  |  | I
4.7.5 | Ensure the delivery team's BIM execution plan is included in the appointment | ISO 19650-2; 5.4.6 | A/R |  |  | I |  | I |  |  | I
4.7.6 | Ensure the delivery team's master information delivery plan (MIDP) is included in the appointment | ISO 19650-2; 5.4.6 | A/R |  |  | I |  | I |  |  | I
4.7.7 | Ensure the project's information protocol is included within the appointment | n/a | A/R |  |  | I |  | I |  |  | I
4.7.8 | Manage change control process associated to lead appointed party(s) appointment documentation | n/a | A/R |  |  | I |  | I |  |  | I
4.8 | Complete appointed party's appointment documents | ISO 19650- 2; 5.4.7
4.8.1 | Complete appointed party's appointment documents for agreement with each appointed party | ISO 19650-2; 5.4.7 |  |  |  | R |  | A/R |  |  | C | I
4.8.2 | Ensure the lead appointed party's exchange information requirements are included in the appointment | ISO 19650-2; 5.4.7 |  |  |  | R |  | A/R |  |  | C | I
4.8.3 | Ensure the project's information standard is included in the appointment with any agreed additions or amendments | ISO 19650-2; 5.4.7 |  |  |  | R |  | A/R |  |  | C | I
4.8.4 | Ensure the project's information production methods and procedures is included in the appointment with any agreed additions or amendments | ISO 19650-2; 5.4.7 |  |  |  | R |  | A/R |  |  | C | I
4.8.5 | Ensure the delivery team's BIM execution plan is included in the appointment | ISO 19650-2; 5.4.7 |  |  |  | R |  | A/R |  |  | C | I
4.8.6 | Ensure the agreed task information delivery plan (TIDP) is included in the appointment | ISO 19650-2; 5.4.7 |  |  |  | R |  | A/R |  |  | C | I
4.8.7 | Ensure the project's information protocol is included within the appointment | n/a |  |  |  | R |  | A/R |  |  | C | I
4.8.8 | Manage change control process associated to appointed party(s) appointment documentation | n/a |  |  |  | R |  | A/R |  |  | C | I

## Appointed Party
Project No: |  | Information management assignment matrix: Building services sub-contractor (Appointed Party)
Key: R Responsible for undertaking activity/task A Accountable for activity/task completion C Consulted during activity/task I Informed following activity/task completion |  | Source | Appointing party |  | Lead appointed party | Subcontractor appointed party | [7 empty] | Appointed party
|  |  | Client | Client's third party | Main Contractor | Lead Designer | Project manager | Mechanical engineer | Electrical engineer | Quantity surveyor | Document controller | CAD technician(s) | BIM specialist | Supply chain task teams
ID Activity/task
6 | Information management process - Collaborative production of information | ISO 19650-2; 5.6
6.1 | Check availability of reference information and shared resources | ISO 19650-2; 5.6.1
6.1.1 | Check that relevant reference information and shared resources is available within the project's common data environment | ISO 19650-2; 5.6.1 |  |  |  | I | I |  |  |  | R | C | A/R | I
6.1.2 | Inform the lead appointed party and assess the potential impact of not having access to reference information and shared resources could have on the task information delivery plan (TIDP) | ISO 19650-2; 5.6.1 |  |  | I | R | A/R |  |  |  |  | C | R
6.2 | Generate information | BS EN ISO 19650- 2:2018; 5.6.2
6.2.1 | Generate information in accordance with respective task information delivery plan (TIDP) | ISO 19650-2; 5.6.2 a) |  |  | I | A/R | R | R | R | R | C | R | R | R
6.2.2 | Coordinate and cross-reference all information with information shared within the project’s common data environment, in accordance with the project’s information production methods and procedures | ISO 19650-2; 5.6.2 c) |  |  | I | R | I | R | R | I | A/R | R | C | R
6.2.3 | Spatially coordinate geometrical models with other geometrical models shared with the appropriate suitability, residing within the project’s common data environment | ISO 19650-2; 5.6.2 d) |  |  | I | I |  | I | I |  | I | A/R | C | R
6.3 | Undertake quality assurance check | ISO 19650-2; 5.6.3
6.3.1 | Undertake a quality assurance check of each information container, in accordance with the project's information production methods and procedures, prior to undertaking a review of the information within it | ISO 19650-2; 5.6.3 |  |  | I | C | I |  |  |  | A/R | R | C | R
6.4 | Review information and approve for sharing | ISO 19650-2; 5.6.4
6.4.1 | Undertake a review of the information within each information container, in accordance with the project's information production methods and procedures, prior to sharing within the project's common data environment | ISO 19650-2; 5.6.4 |  |  | I | A/R | I | R | R | I | I | C | C | C
6.5 | Information model review | ISO 19650-2; 5.6.5
6.5.1 | Undertake a review of the information model, in accordance with the project's information production methods and procedures, to facilitate the continuous coordination of information across each element of the information model | ISO 19650-2; 5.6.5 |  |  | I | R | I | I | I |  | I | I | A/R | I
7 | Information management process - Information model delivery | ISO 19650-2; 5.7
7.1 | Submit information model for lead appointed party authorization | ISO 19650-2; 5.7.1
7.1.1 | Submit information to the lead appointed party for authorization within the project's common data environment | ISO 19650-2; 5.7.1 |  |  | I | R | R | C | C | I | A/R | C | R | I
7.2 | Review and authorize the information model | ISO 19650-2; 5.7.2
7.2.1 | Review the information model in accordance with the project's information production methods and procedures | ISO 19650- 2; 5.7.2 |  |  | A/R | I | I | [5 empty] | I
7.3 | Submit information model for appointing party acceptance | ISO 19650- 2; 5.7.3
7.3.1 | Submit information for appointing party review and acceptance within the project's common data environment | ISO 19650- 2; 5.7.3 | I |  |  | R | R | C | C | I | A/R | C | R
7.4 | Review and accept the information model | ISO 19650- 2; 5.7.4
7.4.1 | Review the information model in accordance with the project's information production methods and procedures | ISO 19650- 2; 5.7.4 | A/R | [9 empty] | A/R
7.4.2 | Produce report at each information exchange of the information model review carried out | n/a | A/R |  | I |  | I | [5 empty] | I | I
8 | Information management process - Project close- out | ISO 19650- 2; 5.8
8.1 | Archive the project information model | ISO 19650- 2; 5.8.1
8.1.1 | Archive the information containers within the project's common data environment in accordance with the project's information production methods and procedures | ISO 19650- 2; 5.8.1 | A/R
8.2 | Capture lessons learned for future projects | ISO 19650- 2; 5.8.2
8.2.1 | Arrange and chair a lessons learned workshop (or include lessons learned within other agreed workshops) in accordance with workshops identified on the project programme | n/a | A/R |  |  |  | I | [5 empty] | I | I
8.2.2 | Capture lessons learned (using the lessons learned template) during the project. The lessons learned should be maintained throughout the project and uploaded to the project’s common data environment or other agreed central knowledge store | ISO 19650- 2; 5.8.2 | A/R |  |  |  | I | [5 empty] | I | I